## REQUIREMENT MATRIX
REQUIREMENTS TRACEABILITY MATRIX
PROJECT MANAGER: | Amit |  |  | PROJECT ID: | AX-EMEA-000302
PROJECT SPONSOR: | SYED NAWKIL |  |  | PROJECT TITLE: | Swag Lab
REQUIREMENT INFORMATION |  |  |  |  | RELATIONSHIP TRACEABILITY
ID | CATEGORY | REQUIREMENT | PRIORITY | SOURCE | BUSINESS OBJECTIVE | DELIVERABLE(S | VERFICATION | VALIDATION
REQ001 | Authentication | The system should allow users to log in with valid credentials. | High | User Requirement | To ensure authorized access to the system. | Login functionality | Testing | Testing
REQ002 | Authentication | The system should display an error message for locked-out users. | Medium | User Requirement | To prevent access for locked-out users. | Error message display | Testing | Testing
REQ003 | Authentication | The system should handle login for users with potential issues. | Medium | User Requirement | To provide support for users experiencing problems during login. | Error handling during login | Testing | Testing
REQ004 | Performance | The system should handle login for users with performance issues. | High | User Requirement | To ensure users with performance issues can still log in efficiently. | Efficient login performance | Testing | Testing
REQ005 | Authentication | The system should display an error message for invalid usernames. | Medium | User Requirement | To notify users of invalid login attempts. | Error message display | Testing | Testing
REQ006 | Authentication | The system should display an error message for invalid passwords. | Medium | User Requirement | To notify users of invalid login attempts. | Error message display | Testing | Testing
REQ007 | Authentication | The system should display an error message for empty usernames. | Low | User Requirement | To prompt users to enter their username. | Error message display | Testing | Testing
REQ008 | Authentication | The system should display an error message for empty passwords. | Low | User Requirement | To prompt users to enter their password. | Error message display | Testing | Testing
REQ009 | Authentication | The system should display an error message for both fields empty. | Low | User Requirement | To prompt users to enter both their username and password. | Error message display | Testing | Testing
REQ010 | Authentication | The system should support "Show Password" functionality. | Medium | User Requirement | To provide users the option to view their password while typing. | Password visibility toggle | Testing | Testing
REQ011 | Authentication | The system should support "Forgot Password" link functionality. | Medium | User Requirement | To provide users with a method to recover their password. | Forgot password link | Testing | Testing
REQ012 | Authentication | The system should handle mixed case usernames. | Low | User Requirement | To ensure flexibility in username input. | Case-insensitive username handling | Testing | Testing
REQ013 | Authentication | The system should handle mixed case passwords. | Low | User Requirement | To ensure flexibility in password input. | Case-insensitive password handling | Testing | Testing
REQ014 | Usability | The system should ensure the login page layout is responsive. | Medium | User Requirement | To provide a consistent user experience across devices. | Responsive login page layout | Testing | Testing
REQ015 | Security | The system should mask the password field. | High | User Requirement | To enhance security by hiding passwords from view. | Masked password input | Testing | Testing
REQ016 | Security | The system should lock the account after multiple failed attempts. | High | User Requirement | To prevent unauthorized access due to brute force attacks. | Account lockout mechanism | Testing | Testing
REQ017 | Security | The system should handle expired sessions appropriately. | High | User Requirement | To ensure security by terminating inactive sessions. | Session expiration handling | Testing | Testing
REQ018 | Usability | The system should support "Remember Me" functionality. | Medium | User Requirement | To provide convenience by remembering user login credentials. | "Remember Me" checkbox | Testing | Testing

## DEFINITIONS
DEFINITIONS
PROJECT MANAGER
The person with responsbility for managing and delivering the project. They will own this log, but may not be the person maintaining it.
PROJECT ID
The project number is assigned by the PMO (Project Management Office) once the project is approved for funding.
PROJECT SPONSOR
The person with ultimate accountablity for the project. They will hold the purse strings.
PROJECT TITLE
The name of the project, this should align with the name given on other project documents (rather than being a nickname).
REQUIREMENT ID
Give each requirement a unique identifier or reference so that it can be easily traced throughout the project life-cycle.
CATEGORY
Provide a category for the requirement typical categories are: functional, non-functional, usability, security, performance, maintainability etc.
REQUIREMENT
Describe the requirement that needs to be met by the project. The requirement might be a product, some product functionality, a service, or a result.
PRIORITY
Provide a priority for the requirement. For example, mandatory, should have, nice to have or high, medium, low.
SOURCE
Enter the name of the stakeholder that identified the requirement.
BUSINESS OBJECTIVE
Document the business objective that this requirement will meet or help to meet. The business objective will come from the project charter or the Project business Case.
DELIVERABLE(S)
List the deliverable or deliverables that will make up this requirement.
VERIFICATION
Explain how you will test that the requirement is completed satisfactorily. For example 99.9% uptime for user acceptance of software.
VALIDATION
Explain how the requirement will be validated or tested. This will often be via user acceptance testing, but it might also be by the achievement of a milestone or perhaps by the completion of a key performance indicator.